## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 5 | 1 | 1 | 1 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Student Data Analysis |  | Project Id: | IP -4064 | Project Manager: | Aarushi Bose |  |  | Assumption | 3 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 3 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2024-06-28 | Project Team Lead: | Aarushi Bose |  |  | Dependency | 4 | 1 | 0 | 1 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 15 |  |  |  |  | 5
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Inability to do required maintenance on time. | Impact on the project schedule and cost. | Have a dedicated maintenance team for the project .The project budget should be considered. | Project Manager | High | 4 | Open | Risk
2 | Risk | Long supply delivery time | Impact on project schedule | Search for vendors who will deliver the resources on timeand within the proposed budget. | Project Manager | Critical | 2 | Closed | Assumption
3 | Risk | Risk of violating data privacy regulations | Illegal spread of confidential data | Ensure compliance with relevant data protection laws (e.g., GDPR, HIPAA). | Project Manager | Critical | 1 | Open | Issue
4 | Risk | Incomplete/Inaccurate Data | Misleading analytical results | Implement data validation and cleaning processes. | Project Manager | High | 3 | Closed | Dependency
5 | Risk | Participant Drop-out | Impact sample size | Maintain regular communication. | Project Manager | Moderate | 5 | Open
6 | Assumption | All required data is complete and accessible | Incomplete data can lead to inaccurate analysis, which may result in flawed decision-making. | Conduct thorough data validation and quality checks before using the data for analysis. | Project Manager | High |  | Closed | Open
7 | Assumption | Sample size is sufficient to draw meaningful conclusions | Insufficient sample size may result in statistically insignificant findings, making it difficult to make reliable conclusions. | Conduct power analysis to determine the required sample size based on the desired level of significance and effect size. | Project Manager | High |  | Closed | Closed
8 | Assumption | Stakeholders Cooperations are met | Lack of stakeholder cooperation can lead to project delays and hinder progress. | Establish clear communication channels and expectations with stakeholders from the beginning. | Stake Holders | Critical |  | Closed
9 | Issue | Data collection delays | Impact on project timelines. | Address by setting clear data collection deadlines. | Project Manager | Critical |  | Closed | Critical
10 | Issue | Technical challenges | Improper functioning of tools and software | Ensure IT support is available. | Technical Manager | High |  | Closed | High
11 | Issue | Interpreting complex results | Complex results challenge proper interpretation | Involve Domain Experts. | Project Manager | Low |  | Closed | Moderate
12 | Dependency | Dependent on the cooperation of universities, internship programs, and other relevant organizations for data sharing. | Lack of cooperation from these organizations may lead to delays in obtaining critical data, hindering research or project timelines. | Establish clear data-sharing agreements and protocols with universities, internship programs, and organizations involved. | Universities | Critical |  | Open | Low
13 | Dependency | Availability of resources such as data analysts, statisticians, and data visualization tools. | A shortage of essential resources can lead to bottlenecks in data analysis and reporting. | Develop resource allocation plans and identify potential skill gaps in advance. | Project Manager | Moderate |  | Open | Negligible
14 | Dependency | Dependent on obtaining any necessary ethical approvals for the study, if applicable. | Failure to obtain ethical approvals can result in legal and reputational issues | Initiate the ethical approval process early in the project planning phase. | Project Manager | High |  | Closed
15 | Dependency | Dependent on the analysis results, which influence the content and format of reports and presentations to stakeholders. | Unforeseen delays or issues in the analysis process can disrupt the development of reports and presentations. | Develop a detailed project plan that includes milestones for data analysis and reporting phases. | Project Manager | Critical |  | Closed
16
17
18
19
20
21
22
23
24