## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Aarushi Bose
PROJECT NAME: | Students Data Analysis
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-06-26
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Data Analysis |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP -4064
PROJECT MANAGER | Aarushi Bose
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-06-04 | Some interns exhibit a decline in engagement in events as they progress in their internships. | Intern Progression | Yes | Develop mentorship programs to maintain intern engagement throughout their internship duration. | Pilot mentorship program with a select group of interns and monitor their engagement levels. | HR Depaertment | Solved | The mentorship program showed positive results in maintaining intern engagement levels.
2 | 2024-06-09 | Interns who receive regular feedback tend to perform better in both scholastic and extracurricular activities. | Feedback Mechanisms | No | Establish a formal feedback system for interns, ensuring that they receive regular feedback from their supervisors. | Implement a feedback system and train supervisors on providing constructive feedback. | Training and Development Team | Pending | The implementation of a feedback system is in progress, and initial results are expected soon.
3 | 2024-06-18 | A high number of interns express uncertainty about their career ambitions during exit interviews. | Career Ambitions | Yes | Conduct career counseling sessions for interns early in their internship to help them clarify their career goals. | Implement career counseling sessions as part of the onboarding process for interns. | Career Development Team | Solved | Career counseling sessions have led to interns having a clearer vision of their career paths.
4 | 2024-06-24 | Interns who actively participate in career development workshops tend to have clearer career ambitions. | Career Development | Yes | Increase the promotion of career development workshops and encourage interns to participate actively. | Develop a marketing campaign for career development workshops and track participation rates. | Career Development Team | Pending | Early data suggests that increased promotion has resulted in higher workshop attendance.
5 | 2024-06-26 | Data shows that intern satisfaction is strongly correlated with their perception of their contributions to meaningful projects. | Intern Satisfaction | No | Assign interns to projects that align with their interests and provide opportunities for meaningful contributions. | Revise the internship project assignment process to ensure better alignment with intern interests. | Internship Program Coordinator | Pending | Implementation is underway to improve the intern project assignment process and enhance overall intern satisfaction.